## Sheet1
TASK | START DATE | DURATION | COMPLETE | END DATE
A. Set deadline for large video post | 2020-11-16 | 1 | 1 | 2020-11-16
B. Specify with group where to post final video | 2020-11-16 | 1 | 1 | 2020-11-16 | X | Y
C. Post large video on required social media | 2020-11-28 | 2 | 2 | 2020-11-30 | 2020-12-04 | 0
D. Set deadline for posting | 2020-11-16 | 1 | 1 | 2020-11-16 | 2020-12-04 | 1
E. Make a list of team members social media accounts | 2020-11-16 | 1 | 1 | 2020-11-16
F. Set meeting time to discuss video quality | 2020-11-19 | 1 | 1 | 2020-11-20
G. Modify and/or post video 1 | 2020-11-20 | 1 | 1 | 2020-11-21
H. Modify and/or post video 2 | 2020-11-20 | 1 | 1 | 2020-11-21
I. Modify and/or post video 3 | 2020-11-20 | 1 | 1 | 2020-11-21
J. Modify and/or post video 4 | 2020-11-20 | 1 | 1 | 2020-11-21
K. Modify and/or post video 5 | 2020-11-20 | 1 | 1 | 2020-11-21
L. Modify and/or post video 6 | 2020-11-20 | 1 | 1 | 2020-11-21
M. Modify and/or post video 7 | 2020-11-20 | 1 | 1 | 2020-11-21
N. Verify all 7 videos are posted | 2020-11-21 | 1 | 1 | 2020-11-21
W. Have required social media set up | 2020-11-17 | 1 | 1 | 2020-11-17
X. Request access to Western Technical College marketing page | 2020-11-20 | 1 | 1 | 2020-11-20
Y. Determine what metrics to keep track of | 2020-11-16 | 1 | 1 | 2020-11-16
Z. Create a schedule to monitor metrics | 2020-11-16 | 1 | 1 | 2020-11-16
AA. Document large video engagements | 2020-11-28 | 2 | 4 | 2020-12-04
AB. Document video 1 engagements | 2020-11-28 | 2 | 4 | 2020-12-04
AC. Document video 2 engagements | 2020-11-28 | 2 | 4 | 2020-12-04
AD. Document video 3 engagements | 2020-11-28 | 2 | 4 | 2020-12-04
AE. Document video 4 engagements | 2020-11-28 | 2 | 4 | 2020-12-04
AF. Document video 5 engagements | 2020-11-28 | 2 | 4 | 2020-12-04
AG. Document video 6 engagements | 2020-11-28 | 2 | 4 | 2020-12-04
AH. Document video 7 engagements | 2020-11-28 | 2 | 4 | 2020-12-04
AI. Choose 3 different careers in marketing | 2020-11-16 | 1 | 1 | 2020-11-16
AJ. Write the job description and responsibilities for all 3 | 2020-11-16 | 1 | 1 | 2020-11-16
AK. Add additional information about the jobs if needed | 2020-11-16 | 1 | 1 | 2020-11-16
AL. Choose 1 of the 3 jobs and discuss with everyone else | 2020-11-16 | 1 | 1 | 2020-11-16
AM. Go over job duties and responsibilities with classmates | 2020-11-16 | 1 | 1 | 2020-11-16
AN. Go on Tiktok and watch some videos on your “for you” page | 2020-11-17 | 1 | 1 | 2020-11-17
AO. Look at those videos and see their hashtags | 2020-11-17 | 1 | 1 | 2020-11-17
AP. Record hashtags you think will help you with your video | 2020-11-17 | 2 | 2 | 2020-11-19
AQ. Create and determine hashtag(s) for all video(s) | 2020-11-19 | 1 | 1 | 2020-11-20
AR. ResearchTikTok and learn how to use | 2020-11-17 | 1 | 1 | 2020-11-17
AS. Look at top creators for more ideas | 2020-11-17 | 1 | 1 | 2020-11-17
AT. Download and set up TikTok | 2020-11-17 | 1 | 1 | 2020-11-17
AU. Choose storyboard template | 2020-11-16 | 1 | 1 | 2020-11-16
AV. Discuss and agree upon storyboard sections/content with team | 2020-11-16 | 1 | 1 | 2020-11-16
AW. Create storyboard | 2020-11-16 | 1 | 1 | 2020-11-16
AX. Discuss and agree upon a consistent format with team | 2020-11-16 | 1 | 1 | 2020-11-16
CF. Create script | 2020-11-16 | 1 | 1 | 2020-11-16
CG. Choose Music (?) | 2020-11-16 | 2 | 2 | 2020-11-18
CH. Choose Props (?) | 2020-11-16 | 3 | 3 | 2020-11-19
BG. Create Video 1 | 2020-11-18 | 1 | 1 | 2020-11-19
BH. Make small edits(Captions, etc) for video 1 | 2020-11-18 | 1 | 1 | 2020-11-19
CI. Create Video 2 | 2020-11-18 | 1 | 1 | 2020-11-19
CJ. Make small edits(Captions, etc) for video 2 | 2020-11-18 | 1 | 1 | 2020-11-19
CK. Create Video 3 | 2020-11-18 | 1 | 1 | 2020-11-19
CL. Make small edits(Captions, etc) for video 3 | 2020-11-18 | 1 | 1 | 2020-11-19
CM. Create Video 4 | 2020-11-18 | 1 | 1 | 2020-11-19
CN. Make small edits(Captions, etc) for video 4 | 2020-11-18 | 1 | 1 | 2020-11-19
CO. Create Video 5 | 2020-11-18 | 1 | 1 | 2020-11-19
CP. Make small edits(Captions, etc) for video 5 | 2020-11-18 | 1 | 1 | 2020-11-19
CQ. Create Video 6 | 2020-11-18 | 1 | 1 | 2020-11-19
CR. Make small edits(Captions, etc) for video 6 | 2020-11-18 | 1 | 1 | 2020-11-19
CS. Create Video 7 | 2020-11-18 | 1 | 1 | 2020-11-19
CT. Make small edits(Captions, etc) for video 7 | 2020-11-18 | 1 | 1 | 2020-11-19
BI. edit and polish video 1 | 2020-11-18 | 1 | 1 | 2020-11-19
BJ. edit and polish video 2 | 2020-11-18 | 1 | 1 | 2020-11-19
BK. edit and polish video 3 | 2020-11-18 | 1 | 1 | 2020-11-19
BL. edit and polish video 4 | 2020-11-18 | 1 | 1 | 2020-11-19
BM. edit and polish video 5 | 2020-11-18 | 1 | 1 | 2020-11-19
BN. edit and polish video 6 | 2020-11-18 | 1 | 1 | 2020-11-19
BO. edit and polish video 7 | 2020-11-18 | 1 | 1 | 2020-11-19
BQ. Send individual video in the Facebook group chat | 2020-11-19 | 1 | 1 | 2020-11-20
BR. Team list 3 glows and grows for video 1 | 2020-11-20 | 1 | 0 | 2020-11-20
BS. Team list 3 glows and grows for video 2 | 2020-11-20 | 1 | 1 | 2020-11-20
BT. Team list 3 glows and grows for video 3 | 2020-11-20 | 1 | 1 | 2020-11-20
BU. Team list 3 glows and grows for video 4 | 2020-11-20 | 1 | 1 | 2020-11-20
BV. Team list 3 glows and grows for video 5 | 2020-11-20 | 1 | 1 | 2020-11-20
BW. Team list 3 glows and grows for video 6 | 2020-11-20 | 1 | 1 | 2020-11-20
BX. Team list 3 glows and grows for video 7 | 2020-11-20 | 1 | 1 | 2020-11-20
BY. Collect all edited and finish videos | 2020-11-21 | 1 | 1 | 2020-11-21
BZ. Format large video according to requirements | 2020-11-21 | 1 | 1 | 2020-11-21
CA. edit/polish | 2020-11-21 | 1 | 1 | 2020-11-21
CB. Send video to group | 2020-11-22 | 1 | 1 | 2020-11-22
CD. Have everyone comment at least 2 grows and glows for the large video | 2020-11-22 | 3 | 3 | 2020-11-25
CE. Send video back to editor(Duncan) to finalize | 2020-11-25 | 3 | 3 | 2020-11-28